## Cover Page
Master Chef
Prepared By:
LIST TEAM MEMBER FULL NAMES
Ammar Sathar 40182146
Navnit Chittoo - 40268729
Joey Chan (40029237)
Haoyang Ni 40310278
Paulina Aguayo Dupin 40299470

## MasterChef sample
Issue # | User Story Title | Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members
#1 | Story 1: User Registration As a new user, I want to register an account so that I can access the MasterChef platform and be asked to input my preferences and dietary information | Create registration page UI | Design and implement user-friendly registration form with email, username, password, confirm password fields | 1 | 3rd February | High |  | Mohammed
#1 |  | Implement frontend validation | Add client-side validation for email format, password strength (min 8 chars, 1 uppercase, 1 number, 1 special char), matching passwords | 1 | 3rd February | High |  | Mohammed
|  | Implement User Preferences/creation flow | Design forms/flow for adding user infomation such as age, date, weight, height, dietary preferences, etc | 2 | 3rd February | Low |  | Mohammed
#1 |  | Create user database schema | Design and implement database table for users (id, email, username, password_hash, created_at, updated_at, is_active) | 1 | 2nd February | High |  | Ammar
#1 |  | Implement backend registration API | Develop POST /api/auth/register endpoint with validation, duplicate checking, password hashing (bcrypt), user creation | 2 | 3rd February | High |  | Paulina
#1 |  | Add email uniqueness validation | Implement backend logic to check if email already exists before registration | 2 |  | Low |  | Haoyang
#1 |  | Implement error handling | Add comprehensive error messages for: duplicate email, weak password, invalid email format, server errors | 1 |  | Low |  | Haoyang
#1 |  | Create unit tests | Write tests for registration validation, password hashing, duplicate user prevention, database insertion | 2 | 4th February | Medium |  | Ammar
#1 |  | Integration testing | Test complete registration flow from frontend to database, verify user creation and data integrity | 1 | 4th February | Medium |  | Paulina
#2 | Story 2: User Login As a registered user, I want to log in to my account so that I can access my personalized meal plans | Create login page UI | Design and implement login form with email, password fields, 'Remember Me' checkbox, 'Forgot Password' link placeholder | 1 | 3rd February | High |  | Joey
#2 |  | Implement frontend validation | Add client-side validation for email format and required fields before submission | 1 | 3rd February | High |  | Joey
#2 |  | Implement backend authentication API | Develop POST /api/auth/login endpoint with credential verification, password comparison, session/token generation (Use BetterAuth) | 2 | 3rd February | High |  | Navnit
#2 |  | Implement session management | Set up session handling for maintaining user authentication state (Cookie) | 1 | 3rd February | Low |  | Navnit
#2 |  | Add authentication error handling | Implement error messages for: invalid credentials, account not found | 1 | 3rd February | Medium |  | Haoyang
#2 |  | Implement logout functionality | Add logout endpoint that invalidates session/token and clears client-side authentication data | 1 | 4th february | Low |  | Navnit
#2 |  | Create unit tests | Write tests for login validation, credential verification, token generation, invalid login attempts | 1 | 4th february | Medium |  | Ammar
#2 |  | Integration testing | Test complete login flow, session persistence, protected route access, logout functionality | 2 | 4th february | Medium |  | Ammar
#3 | Story 3: Profile Management As a logged-in user, I want to manage my dietary preferences and allergies for personalized recommendations | Create profile page UI | Design and implement profile management interface with sections for: personal info, dietary preferences, allergies | 2 | 4th february | Medium | Low | Mohammed
#3 |  | Modify dietary preferences form | Modify form with checkboxes/multi-select for: Vegetarian, Vegan, Gluten-free, Dairy-free, Keto, Paleo, Pescatarian, Halal, Kosher | 1 | 4th february | Medium | Low | Mohammed
#3 |  | Modify allergies input field | Implement text input or tag system for users to enter food allergies (e.g., nuts, shellfish, soy, eggs) | 1 | 4th february | Medium | Low | Mohammed
#3 |  | Extend user database schema | Add columns to user table for dietary_preferences (JSON/array), allergies (JSON/array), updated_at timestamp | 2 | 5th February | Medium | Low | Joey
#3 |  | Implement profile update API | Develop PUT /api/user/profile endpoint to update user preferences, validate input, save to database | 1.5 | 5th February | Medium | Low | Paulina
#3 |  | Add profile update validation | Validate dietary preferences from allowed list, allergies properly formatted, prevent malicious input |  | 5th February | Medium | Low | Navnit
#3 |  | Implement edit/view mode toggle | Add functionality to switch between viewing profile and editing mode, with save/cancel buttons | 2 | 5th February | Medium | Low | Haoyang
#3 |  | Create unit tests | Write tests for profile update validation, data retrieval, preference saving, input sanitization | 1 | 5th February | Medium | Low | Ammar
#3 |  | Integration testing | Test complete profile management flow: view, edit, save, reload to verify persistence | 2 | 5th February | Medium | Low | Ammar

## Product Backlog 1st sample
Issue # | User story | Associated Tasks | Story points associated to a US | Priority | Risk (High, Medium, Low) | Responsible | Due date
1 | Once website is clicked, user will see the login page | -Create UI for a login page or sign up page (email, password) -Verify that the 2 password inputs match in case of signing up -Ask for security question and store it in the database -Create an option for the user to reset the password with the security question | 6 | HIGH | HIGH - Part of main function of website. Will determine if the user is a buyer/renter, broker, or admin | Front end: - Abilash - Killian - Nabih | 2023-10-12
2 | User's information is saved during registration and user is authenticated user during login | -Create a function that saves user name and password in the database during registration -Create a function that retrives the information from the database which will allow to authenticate user during login | 7 | HIGH | HIGH - User information not saved in the database. User enters false information (misidentification). | Back end: - Joerex - Kate - Peno | 2023-10-20
3 | User has a user-friendly interface of a home page with filter bar | -Sketch a wireframe or prototype of the homepage layout -Create a home page with a basic an initial design for the rest of the pages including headers, navigation menus, search forms, filter bar | 5 | MEDIUM | LOW - Can be easily revised and adjusted later on based on user feedback | Front end: - Abilash - Killian - Nabih | 2023-10-27
4 | User will see all the potential properties as a list | -Research houses and write them in a google doc as a list -For each house, indicate the price, location, lot and house area, year built, # of rooms and bathrooms, schools, parks, stores, and hospitals nearby, parking, transportation, extras (swimming pool, etc) | 4 | MEDIUM | LOW - We can always complete the research after Oct 27. It is not required to have every info accurate. | Back end: - Joerex - Kate - Peno | 2023-10-27
5 | User will see a 'Broker's' page and will be able to search for a specific brokert | -Create ‘brokers’ page that shows the list of all brokers in cards similar to the properties -Search feature on the ‘brokers’ page; searching based on username (same as property search) -Add: email and phone number to brokers, that can be modified in profile page | 3 | MEDIUM | MEDIUM - The demand received from product owner (TA) is high regarding this feature | -Joerex -Abilash | 2023-11-06
6 | User will be able to make an offer on a property card inputting an offer amount in a modal/form | -Add button to searched property cards: ‘make offer’ -‘make offer’ button pops up a modal/form where the user enters a number and submits -Create new object in the database: offers -Define structure of offers in backend: (offer creator, amount, status, property, (broker)) -Submitting an offer creates an offer in the database (default status: “pending”) | 5 | MEDIUM | HIGH - Needs to be completed before November 3, Isusue # 7 cannot begin before the completion of this | -Kateryna -Killian | 2023-11-03
7 | User will see a dedicated 'Offers' page with SENT and RECEIVED sections | -Sent section shows all offers that the user created -Received section is for brokers, showing all offers for the creator broker's property -Create accept and reject buttons on each offer on the received section -Accept button sets the offer status to “accepted” -Accept button sets the offer status to “rejected” | 4 | MEDIUM | HIGH - Data integrity concerns (lost data), financial concerns | -Nabih -Peno | 2023-11-08
8 | User will have the ability to use a mortgage calculator for the listing of the choice | -Create form where user can input various fields such as down payment, interest rate, etc. -Clicking the button shows/hides the form -Logic to calculate and return the resulting mortgage information -Nicely display the mortgage information to the user as a table or any format of choice | 4 | HIGH | HIGH - Accurate logic and calculations are crucial for user trust; The demand received from product owner (TA) is high regarding this feature | - Joerex -Kilian | 2023-11-23
9 | Brokers will be able to add a counteroffering that the buyer can accept or reject | -Fix bug for multiple offers on same property -Add counteroffering capability from broker -Users can accept or reject a broker’s counteroffer | 3 | MEDIUM | HIGH - Data integrity concerns (lost data), financial concerns | -Nabih -Peno | 2023-11-23
10 | User will benefit from an enhanced user interface | -CSS style revamping for elements -Add colour and life to the site -Better images -Animations for certain elements -Replace all default JS alerts() with something better | 2 | LOW | LOW - Introducing new UI elements or interactions should not affect performance | -Abilash -Kateryna | 2023-11-25
|  | Total: | 43

## Sprint Plan
Issue # | User Story Title | Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Risk Explanation | Dependencies | Assigned Members
#1 | Story 1: User Registration As a new user, I want to register an account so that I can access the MealMajor platform and be asked to input my preferences and dietary information. | Create registration page UI | Design and implement user-friendly registration form with email, username, password, confirm password fields. | 1 | 3rd February | High | Medium | UI is the entry point for all registration tasks; delays here cascade downstream. | None | Mohammed
#1 |  | Implement frontend validation | Add client-side validation for email format, password strength (min 8 chars, 1 uppercase, 1 number, 1 special char), matching passwords. | 1 | 3rd February | High | Low | Straightforward rule-based logic; low chance of blockers. | Create registration page UI | Mohammed
#1 |  | Implement User Preferences / creation flow | Design forms/flow for adding user information such as age, date, weight, height, dietary preferences, etc. | 2 | 3rd February | Medium | Low | Can be added after core registration works; isolated form component. | Create registration page UI | Mohammed
#1 |  | Create user database schema | Design and implement database table for users (id, email, username, password_hash, created_at, updated_at, is_active). | 1 | 2nd February | High | Medium | Schema defines the data contract; any design change here ripples into the API and tests. | None | Ammar
#1 |  | Implement backend registration API | Develop POST /api/auth/register endpoint with validation, duplicate checking, password hashing (bcrypt), user creation. | 2 | 3rd February | High | High | Core backend logic; bugs here break registration end-to-end and block integration tests. | Create user database schema | Paulina
#1 |  | Add email uniqueness validation | Implement backend logic to check if email already exists before registration. | 2 | 3rd February | Medium | Low | Relies on a single DB query; well-understood pattern. | Create user database schema, Implement backend registration API | Haoyang
#1 |  | Implement error handling | Add comprehensive error messages for: duplicate email, weak password, invalid email format, server errors. | 1 | 3rd February | Medium | Low | Error messages are polish; core flow works without them. | Implement backend registration API | Haoyang
#1 |  | Create unit tests | Write tests for registration validation, password hashing, duplicate user prevention, database insertion. | 2 | 4th February | Medium | Low | Tests are written after the code they cover; isolated from other stories. | Implement backend registration API, Create user database schema | Ammar
#1 |  | Integration testing | Test complete registration flow from frontend to database; verify user creation and data integrity. | 1 | 4th February | High | Medium | End-to-end flow — any broken link (UI → API → DB) surfaces here. | Create registration page UI, Implement frontend validation, Implement backend registration API, Create unit tests | Ammar
#2 | Story 2: User Login As a registered user, I want to log in to my account so that I can access my personalized meal plans. | Create login page UI | Design and implement login form with email, password fields, 'Remember Me' checkbox, 'Forgot Password' link placeholder. | 1 | 3rd February | High | Low | Simple, self-contained UI component; low technical risk. | None | Joey
#2 |  | Implement frontend validation | Add client-side validation for email format and required fields before submission. | 1 | 3rd February | High | Low | Straightforward validation; mirrors registration pattern already built. | Create login page UI | Joey
#2 |  | Implement backend authentication API | Develop POST /api/auth/login endpoint with credential verification, password comparison, session/token generation (Use BetterAuth). | 2 | 3rd February | High | High | Central auth logic; failure blocks session management, logout, and all protected routes. | Create user database schema (Story 1) | Navnit
#2 |  | Implement session management | Set up session handling for maintaining user authentication state (Cookie). | 1 | 3rd February | High | Medium | Cookie-based sessions must be secure; misconfiguration is a common source of bugs. | Implement backend authentication API | Navnit
#2 |  | Add authentication error handling | Implement error messages for: invalid credentials, account not found. | 1 | 3rd February | Medium | Low | Error messages are polish on top of a working auth flow. | Implement backend authentication API | Haoyang
#2 |  | Implement logout functionality | Add logout endpoint that invalidates session/token and clears client-side authentication data. | 1 | 4th February | Medium | Low | Single endpoint; depends only on session management working correctly. | Implement session management | Navnit
#2 |  | Create unit tests | Write tests for login validation, credential verification, token generation, invalid login attempts. | 1 | 4th February | Medium | Low | Isolated test suite; no cross-story risk. | Implement backend authentication API | Ammar
#2 |  | Integration testing | Test complete login flow, session persistence, protected route access, logout functionality. | 2 | 4th February | High | Medium | Exercises the full auth pipeline — any broken step is caught here. | Create login page UI, Implement frontend validation, Implement backend authentication API, Implement session management, Implement logout functionality, Create unit tests | Ammar
#3 | Story 3: Profile Management As a logged-in user, I want to manage my dietary preferences and allergies for personalized recommendations. | Create profile page UI | Design and implement profile management interface with sections for: personal info, dietary preferences, allergies. | 2 | 4th February | High | Low | Foundation UI for the entire profile story; straightforward layout work. | Implement backend authentication API (Story 2) — user must be logged in | Mohammed
#3 |  | Modify dietary preferences form | Modify form with checkboxes/multi-select for: Vegetarian, Vegan, Gluten-free, Dairy-free, Keto, Paleo, Pescatarian, Halal, Kosher. | 1 | 4th February | Medium | Low | UI-only change on top of an existing form; low complexity. | Create profile page UI | Mohammed
#3 |  | Modify allergies input field | Implement text input or tag system for users to enter food allergies (e.g., nuts, shellfish, soy, eggs). | 1 | 4th February | Medium | Low | Parallel to dietary preferences; isolated input component. | Create profile page UI | Mohammed
#3 |  | Extend user database schema | Add columns to user table for dietary_preferences (JSON/array), allergies (JSON/array), updated_at timestamp. | 2 | 5th February | High | Medium | Schema change affects the profile API and all downstream reads; must be done before the API is built. | Create user database schema (Story 1) | Joey
#3 |  | Implement profile update API | Develop PUT /api/user/profile endpoint to update user preferences, validate input, save to database. | 2 | 5th February | High | Medium | Core backend for profile; validation and DB write both depend on it. | Extend user database schema | Paulina
#3 |  | Add profile update validation | Validate dietary preferences from allowed list, allergies properly formatted, prevent malicious input. | 1 | 5th February | Medium | Low | Rule-based whitelist validation; low technical risk. | Implement profile update API | Navnit
#3 |  | Implement edit/view mode toggle | Add functionality to switch between viewing profile and editing mode, with save/cancel buttons. | 2 | 5th February | Medium | Low | UI state toggle; does not affect data flow. | Create profile page UI | Haoyang
#3 |  | Create unit tests | Write tests for profile update validation, data retrieval, preference saving, input sanitization. | 1 | 5th February | Medium | Low | Isolated test suite covering profile logic only. | Implement profile update API, Add profile update validation | Ammar
#3 |  | Integration testing | Test complete profile management flow: view, edit, save, reload to verify persistence. | 2 | 5th February | High | Medium | End-to-end profile flow — requires UI, API, and DB all working together. | Create profile page UI, Modify dietary preferences form, Modify allergies input field, Implement profile update API, Add profile update validation, Implement edit/view mode toggle, Create unit tests | Ammar