## Cover Page
Master Chef
Prepared By:
LIST TEAM MEMBER FULL NAMES
Ammar Sathar 40182146
Navnit Chittoo - 40268729
Joey Chan (40029237)
Haoyang Ni 40310278
Paulina Aguayo Dupin 40299470
Charrat Mohamed taha 40314694

## Sprint 1 Plan
Issue # | User Story Title | Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Risk Explanation | Dependencies | Assigned Members
#1 | Story 1: User Registration As a new user, I want to register an account so that I can access the MealMajor platform and be asked to input my preferences and dietary information. | Create registration page UI | Design and implement user-friendly registration form with email, username, password, confirm password fields. | 1 | 3rd February | High | Medium | UI is the entry point for all registration tasks; delays here cascade downstream. | None | Mohammed
#1 |  | Implement frontend validation | Add client-side validation for email format, password strength (min 8 chars, 1 uppercase, 1 number, 1 special char), matching passwords. | 1 | 3rd February | High | Low | Straightforward rule-based logic; low chance of blockers. | Create registration page UI | Mohammed
#1 |  | Implement User Preferences / creation flow | Design forms/flow for adding user information such as age, date, weight, height, dietary preferences, etc. | 2 | 3rd February | Medium | Low | Can be added after core registration works; isolated form component. | Create registration page UI | Mohammed
#1 |  | Create user database schema | Design and implement database table for users (id, email, username, password_hash, created_at, updated_at, is_active). | 1 | 2nd February | High | Medium | Schema defines the data contract; any design change here ripples into the API and tests. | None | Ammar
#1 |  | Implement backend registration API | Develop POST /api/auth/register endpoint with validation, duplicate checking, password hashing (bcrypt), user creation. | 2 | 3rd February | High | High | Core backend logic; bugs here break registration end-to-end and block integration tests. | Create user database schema | Paulina
#1 |  | Add email uniqueness validation | Implement backend logic to check if email already exists before registration. | 2 | 3rd February | Medium | Low | Relies on a single DB query; well-understood pattern. | Create user database schema, Implement backend registration API | Haoyang
#1 |  | Implement error handling | Add comprehensive error messages for: duplicate email, weak password, invalid email format, server errors. | 1 | 3rd February | Medium | Low | Error messages are polish; core flow works without them. | Implement backend registration API | Haoyang
#1 |  | Create unit tests | Write tests for registration validation, password hashing, duplicate user prevention, database insertion. | 2 | 4th February | Medium | Low | Tests are written after the code they cover; isolated from other stories. | Implement backend registration API, Create user database schema | Ammar
#1 |  | Integration testing | Test complete registration flow from frontend to database; verify user creation and data integrity. | 1 | 4th February | High | Medium | End-to-end flow — any broken link (UI → API → DB) surfaces here. | Create registration page UI, Implement frontend validation, Implement backend registration API, Create unit tests | Ammar
#2 | Story 2: User Login As a registered user, I want to log in to my account so that I can access my personalized meal plans. | Create login page UI | Design and implement login form with email, password fields, 'Remember Me' checkbox, 'Forgot Password' link placeholder. | 1 | 3rd February | High | Low | Simple, self-contained UI component; low technical risk. | None | Joey
#2 |  | Implement frontend validation | Add client-side validation for email format and required fields before submission. | 1 | 3rd February | High | Low | Straightforward validation; mirrors registration pattern already built. | Create login page UI | Joey
#2 |  | Implement backend authentication API | Develop POST /api/auth/login endpoint with credential verification, password comparison, session/token generation (Use BetterAuth). | 2 | 3rd February | High | High | Central auth logic; failure blocks session management, logout, and all protected routes. | Create user database schema (Story 1) | Navnit
#2 |  | Implement session management | Set up session handling for maintaining user authentication state (Cookie). | 1 | 3rd February | High | Medium | Cookie-based sessions must be secure; misconfiguration is a common source of bugs. | Implement backend authentication API | Navnit
#2 |  | Add authentication error handling | Implement error messages for: invalid credentials, account not found. | 1 | 3rd February | Medium | Low | Error messages are polish on top of a working auth flow. | Implement backend authentication API | Haoyang
#2 |  | Implement logout functionality | Add logout endpoint that invalidates session/token and clears client-side authentication data. | 1 | 4th February | Medium | Low | Single endpoint; depends only on session management working correctly. | Implement session management | Navnit
#2 |  | Create unit tests | Write tests for login validation, credential verification, token generation, invalid login attempts. | 1 | 4th February | Medium | Low | Isolated test suite; no cross-story risk. | Implement backend authentication API | Ammar
#2 |  | Integration testing | Test complete login flow, session persistence, protected route access, logout functionality. | 2 | 4th February | High | Medium | Exercises the full auth pipeline — any broken step is caught here. | Create login page UI, Implement frontend validation, Implement backend authentication API, Implement session management, Implement logout functionality, Create unit tests | Ammar
#3 | Story 3: Profile Management As a logged-in user, I want to manage my dietary preferences and allergies for personalized recommendations. | Create profile page UI | Design and implement profile management interface with sections for: personal info, dietary preferences, allergies. | 2 | 4th February | High | Low | Foundation UI for the entire profile story; straightforward layout work. | Implement backend authentication API (Story 2) — user must be logged in | Mohammed
#3 |  | Modify dietary preferences form | Modify form with checkboxes/multi-select for: Vegetarian, Vegan, Gluten-free, Dairy-free, Keto, Paleo, Pescatarian, Halal, Kosher. | 1 | 4th February | Medium | Low | UI-only change on top of an existing form; low complexity. | Create profile page UI | Mohammed
#3 |  | Modify allergies input field | Implement text input or tag system for users to enter food allergies (e.g., nuts, shellfish, soy, eggs). | 1 | 4th February | Medium | Low | Parallel to dietary preferences; isolated input component. | Create profile page UI | Mohammed
#3 |  | Extend user database schema | Add columns to user table for dietary_preferences (JSON/array), allergies (JSON/array), updated_at timestamp. | 2 | 5th February | High | Medium | Schema change affects the profile API and all downstream reads; must be done before the API is built. | Create user database schema (Story 1) | Joey
#3 |  | Implement profile update API | Develop PUT /api/user/profile endpoint to update user preferences, validate input, save to database. | 2 | 5th February | High | Medium | Core backend for profile; validation and DB write both depend on it. | Extend user database schema | Paulina
#3 |  | Add profile update validation | Validate dietary preferences from allowed list, allergies properly formatted, prevent malicious input. | 1 | 5th February | Medium | Low | Rule-based whitelist validation; low technical risk. | Implement profile update API | Navnit
#3 |  | Implement edit/view mode toggle | Add functionality to switch between viewing profile and editing mode, with save/cancel buttons. | 2 | 5th February | Medium | Low | UI state toggle; does not affect data flow. | Create profile page UI | Haoyang
#3 |  | Create unit tests | Write tests for profile update validation, data retrieval, preference saving, input sanitization. | 1 | 5th February | Medium | Low | Isolated test suite covering profile logic only. | Implement profile update API, Add profile update validation | Ammar
#3 |  | Integration testing | Test complete profile management flow: view, edit, save, reload to verify persistence. | 2 | 5th February | High | Medium | End-to-end profile flow — requires UI, API, and DB all working together. | Create profile page UI, Modify dietary preferences form, Modify allergies input field, Implement profile update API, Add profile update validation, Implement edit/view mode toggle, Create unit tests | Ammar

## Sprint 2 Plan
Issue # | User Story Title | Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Risk Explanation | Dependencies | Assigned Members
#2 | Story 2: User Login As a registered user, I want to log in to my account so that I can access my personalized meal plans. | Implement backend authentication API | Develop POST /api/auth/login endpoint with credential verification, password comparison, session/token generation (Use BetterAuth).Google and github authentification | 2 | 17th February | High | High | Central auth logic; failure blocks session management, logout, and all protected routes. | Create user database schema (Story 1) | Nick
#2 |  | Implement session management | Set up session handling for maintaining user authentication state (Cookie). | 1 | 17th February | High | Medium | Cookie-based sessions must be secure; misconfiguration is a common source of bugs. | Implement backend authentication API | Nick
#3 | Story 3: Profile Management As a logged-in user, I want to manage my dietary preferences and allergies for personalized recommendations. | Create profile page UI | Design and implement profile management interface with sections for: personal info, dietary preferences, allergies. | 2 | 17th February | High | Low | Foundation UI for the entire profile story; straightforward layout work. | Implement backend authentication API (Story 2) — user must be logged in | Mohammed
#3 |  | Modify dietary preferences form | Modify form with checkboxes/multi-select for: Vegetarian, Vegan, Gluten-free, Dairy-free, Keto, Paleo, Pescatarian, Halal, Kosher. | 1 | 15th February | Medium | Low | UI-only change on top of an existing form; low complexity. | Create profile page UI | Mohammed
#3 |  | Modify allergies input field | Implement text input or tag system for users to enter food allergies (e.g., nuts, shellfish, soy, eggs). | 1 | 15th February | Medium | Low | Parallel to dietary preferences; isolated input component. | Create profile page UI | Mohammed
#3 |  | Extend user database schema | Add columns to user table for dietary_preferences (JSON/array), allergies (JSON/array), updated_at timestamp. | 2 | 10th February | High | Medium | Schema change affects the profile API and all downstream reads; must be done before the API is built. | Create user database schema (Story 1) | Paulina
#3 |  | Implement profile update API | Develop PUT /api/user/profile endpoint to update user preferences, validate input, save to database. | 2 | 12th February | High | Medium | Core backend for profile; validation and DB write both depend on it. | Extend user database schema | Paulina
#3 |  | Add profile update validation | Validate dietary preferences from allowed list, allergies properly formatted, prevent malicious input. | 1 | 12th February | Medium | Low | Rule-based whitelist validation; low technical risk. | Implement profile update API | Mohammed
#3 |  | Implement edit/view mode toggle | Add functionality to switch between viewing profile and editing mode, with save/cancel buttons. | 2 | 15th February | Medium | Low | UI state toggle; does not affect data flow. | Create profile page UI | Mohammed
#3 |  | Create unit tests | Write tests for profile update validation, data retrieval, preference saving, input sanitization. | 1 | 17thFebruary | Medium | Low | Isolated test suite covering profile logic only. | Implement profile update API, Add profile update validation | Ammar
#3 |  | Integration testing | Test complete profile management flow: view, edit, save, reload to verify persistence. | 2 | 17th February | High | Medium | End-to-end profile flow — requires UI, API, and DB all working together. | Create profile page UI, Modify dietary preferences form, Modify allergies input field, Implement profile update API, Add profile update validation, Implement edit/view mode toggle, Create unit tests | Ammar
US.04 | Story 4: Create, Edit, and Delete Recipes As a logged-in user, I want to create, edit, and delete my own recipes so that I can manage a personal collection of meals with full attribute details. | Create recipe database schema | Design and implement the recipes table: id, user_id (FK), title, description, ingredients (JSON), prep_time (mins), cook_time (mins), steps (JSON), cost, difficulty (easy/medium/hard), dietary_tags (JSON), created_at, updated_at. | 2 | 13th February | High | High | Schema is the foundation for all recipe features; a design flaw here cascades across all stories. | User database schema (Sprint 1 Task.04) | Paulina
US.04 |  | Implement Create Recipe API | Develop POST /api/recipes endpoint. Validate all required fields, associate recipe with the authenticated user, and persist to the database. | 2 | 15th February | High | High | Core write operation; errors here break Create, Edit, and downstream search/filter. | Create recipe database schema | Paulina
US.04 |  | Implement Edit Recipe API | Develop PUT /api/recipes/:id endpoint. Verify requesting user owns the recipe, validate updated fields, and persist changes. | 2 | 15th February | High | Medium | Ownership check is critical; missing it would be a security issue. | Implement Create Recipe API | Paulina
US.04 |  | Implement Delete Recipe API | Develop DELETE /api/recipes/:id endpoint. Verify ownership, soft-delete or hard-delete the record, and return appropriate confirmation. | 1 | 15th February | High | Low | Single endpoint; straightforward once ownership logic is in place. | Implement Edit Recipe API | Paulina
US.04 |  | Build Create Recipe UI form | Design and implement the recipe creation form with fields for: title, description, ingredients (dynamic list), prep time, cook time, steps (ordered list), cost, difficulty selector, and dietary tags. | 3 | 16th February | High | Medium | Complex dynamic form (ingredients/steps as lists); state management requires care. | None | Navnit
US.04 |  | Build Edit Recipe UI form | Re-use the Create form pre-populated with existing recipe data. Add save and cancel buttons; ensure only the recipe owner sees the edit option. | 2 | 17th February | High | Medium | Depends on Create form component being reusable; tight coupling is a risk. | Build Create Recipe UI form, Implement Edit Recipe API | Joey
US.04 |  | Build Delete Recipe UI confirmation | Add a delete button visible only to the recipe owner with a confirmation modal before the DELETE API call is made. | 1 | 17th February | Medium | Low | UI-only change on top of the existing recipe card. | Build Edit Recipe UI form, Implement Delete Recipe API | Joey
US.04 |  | Frontend validation for recipe forms | Add client-side validation: title required, prep/cook time must be positive integers, at least one ingredient required, cost must be a positive number. | 1 | 16th February | Medium | Low | Rule-based validation; mirrors the pattern established in Sprint 1 auth forms. | Build Create Recipe UI form | Navnit
US.04 |  | Create unit tests — Recipe CRUD | Write unit tests for recipe creation, update, delete, ownership validation, and input sanitization. | 2 | 17th February | Medium | Low | Isolated test suite; no cross-story risk. | Implement Create Recipe API, Implement Edit Recipe API, Implement Delete Recipe API | Ammar
US.04 |  | Integration testing — Recipe CRUD | Test the full create → edit → delete lifecycle from the UI through to the database. Verify ownership enforcement and data persistence at each step. | 2 | 17th February | High | Medium | End-to-end flow covering three API endpoints and two UI forms simultaneously. | Build Create Recipe UI form, Build Edit Recipe UI form, Build Delete Recipe UI confirmation, Frontend validation for recipe forms, Create unit tests — Recipe CRUD | Ammar