## Sprint 1 Plan
Issue # | User Story Title | Task Title | Task Description | Story Points (1-5) | Due Date | Priority | Risk | Assigned Members
#US.01 | Story 1: User Registration As a new user, I want to register an account so that I can access the MealMajor platform | Create registration page UI | Design and implement user-friendly registration form with email, username, password, confirm password fields | 3 | Week 2 | High | Low - Standard web form | [Member 1]
#US.01 |  | Implement frontend validation | Add client-side validation for email format, password strength (min 8 chars, 1 uppercase, 1 number, 1 special char), matching passwords | 2 | Week 2 | High | Low - Standard validation libraries | [Member 1]
#US.01 |  | Create user database schema | Design and implement database table for users (id, email, username, password_hash, created_at, updated_at, is_active) | 2 | Week 2 | High | Medium - Must support future features | [Member 2]
#US.01 |  | Implement backend registration API | Develop POST /api/auth/register endpoint with validation, duplicate checking, password hashing (bcrypt), user creation | 4 | Week 3 | High | Medium - Security critical | [Member 2]
#US.01 |  | Add email uniqueness validation | Implement backend logic to check if email already exists before registration | 2 | Week 3 | High | Low - Simple database query | [Member 2]
#US.01 |  | Implement error handling | Add comprehensive error messages for: duplicate email, weak password, invalid email format, server errors | 2 | Week 3 | Medium | Low - Standard error handling | [Member 1]
#US.01 |  | Create unit tests | Write tests for registration validation, password hashing, duplicate user prevention, database insertion | 3 | Week 3 | High | Low - Using JUnit/Jest | [Member 3]
#US.01 |  | Integration testing | Test complete registration flow from frontend to database, verify user creation and data integrity | 2 | Week 4 | High | Medium - May uncover issues | [Member 3]
#US.02 | Story 2: User Login As a registered user, I want to log in to my account so that I can access my personalized meal plans | Create login page UI | Design and implement login form with email, password fields, 'Remember Me' checkbox, 'Forgot Password' link placeholder | 2 | Week 2 | High | Low - Standard login form | [Member 1]
#US.02 |  | Implement frontend validation | Add client-side validation for email format and required fields before submission | 1 | Week 2 | High | Low - Basic validation | [Member 1]
#US.02 |  | Implement backend authentication API | Develop POST /api/auth/login endpoint with credential verification, password comparison, session/token generation | 4 | Week 3 | High | High - Security critical authentication | [Member 2]
#US.02 |  | Implement session management | Set up session handling or JWT token generation for maintaining user authentication state | 3 | Week 3 | High | Medium - Must be secure | [Member 2]
#US.02 |  | Add authentication error handling | Implement error messages for: invalid credentials, account not found, inactive account, too many attempts | 2 | Week 3 | High | Low - Standard error responses | [Member 2]
#US.02 |  | Create protected route middleware | Implement middleware to verify authentication tokens and protect routes requiring login | 3 | Week 3 | High | Medium - Prevent unauthorized access | [Member 4]
#US.02 |  | Implement logout functionality | Add logout endpoint that invalidates session/token and clears client-side authentication data | 2 | Week 3 | Medium | Low - Simple session termination | [Member 4]
#US.02 |  | Create unit tests | Write tests for login validation, credential verification, token generation, invalid login attempts | 3 | Week 3 | High | Low - Standard testing patterns | [Member 3]
#US.02 |  | Integration testing | Test complete login flow, session persistence, protected route access, logout functionality | 2 | Week 4 | High | Medium - Critical for security | [Member 3]
#US.03 | Story 3: Profile Management As a logged-in user, I want to manage my dietary preferences and allergies for personalized recommendations | Create profile page UI | Design and implement profile management interface with sections for: personal info, dietary preferences, allergies | 3 | Week 3 | Medium | Low - Standard form interface | [Member 1]
#US.03 |  | Add dietary preferences form | Create form with checkboxes/multi-select for: Vegetarian, Vegan, Gluten-free, Dairy-free, Keto, Paleo, Pescatarian, Halal, Kosher | 2 | Week 3 | Medium | Low - Simple form controls | [Member 1]
#US.03 |  | Add allergies input field | Implement text input or tag system for users to enter food allergies (e.g., nuts, shellfish, soy, eggs) | 2 | Week 3 | Medium | Low - Standard input field | [Member 1]
#US.03 |  | Extend user database schema | Add columns to user table for dietary_preferences (JSON/array), allergies (JSON/array), updated_at timestamp | 2 | Week 3 | Medium | Low - Database schema extension | [Member 2]
#US.03 |  | Implement profile update API | Develop PUT /api/user/profile endpoint to update user preferences, validate input, save to database | 3 | Week 3 | Medium | Medium - Validate and sanitize input | [Member 2]
#US.03 |  | Implement profile retrieval API | Develop GET /api/user/profile endpoint to fetch current user's profile data including preferences and allergies | 2 | Week 3 | Medium | Low - Simple database query | [Member 2]
#US.03 |  | Add profile update validation | Validate dietary preferences from allowed list, allergies properly formatted, prevent malicious input | 2 | Week 3 | Medium | Medium - Input validation security | [Member 4]
#US.03 |  | Implement edit/view mode toggle | Add functionality to switch between viewing profile and editing mode, with save/cancel buttons | 2 | Week 4 | Low | Low - Frontend state management | [Member 1]
#US.03 |  | Create unit tests | Write tests for profile update validation, data retrieval, preference saving, input sanitization | 2 | Week 4 | Medium | Low - Standard testing | [Member 3]
#US.03 |  | Integration testing | Test complete profile management flow: view, edit, save, reload to verify persistence | 2 | Week 4 | Medium | Low - Verify data persistence | [Member 3]
Total Story Points: |  |  |  | 64